## 22-23
SINGARA CHENNAI 2.0 - PARKS&PLAYFIELD - 2022-23 COMPLETED LIST
Sl. No | Zone | Div | Location | Duaration | Physical Progress (%) | Financial Progress
[6 empty] | Last Review Amt in Lakhs | Now Amt in Lakhs | Total Amt in Lakhs | Bill received
1 | 2 | 15 | Formation of Sponge Park at Manali New Town Block no -54 CPS-6 | 3 months | 100% | 0 | 6.59 | 6.59 | 1st & Final Bill received on 29.09.23
2 | 2 | 15 | Formation of Sponge Park at Manali New Town Block no -29 & 30 CPS-9 | 3 months | 100% | 0 | 7.18 | 7.18 | 1st & Final Bill received on 29.09.23
3 | 2 | 15 | Formation of Sponge Park at Manali New Town Block No-65 CPS-8. | 3 months | 100% | 0 | 5.56 | 5.56 | 1st & Final Bill received on 29.09.23
4 | 2 | 15 | Formation of Sponge Park at Manali New Town Block No-63 CPS-7 | 3 months | 100% | 0 | 7.35 | 7.35 | 1st & Final Bill received on 29.09.23
5 | 2 | 16 | Formation of Sponge Park at Manali New Town Block-134 & 135 CPS-1 Park | 3 months | 100% | 0 | 7.4 | 7.4 | 1st & Final Bill received on 12.10.23
6 | 2 | 16 | Formation of Sponge Park at Manali New Town Block 100 &101 CPS-2 Park | 3 months | 100% | 0 | 6.48 | 6.48 | 1st & Final Bill received on 12.10.23
7 | 2 | 16 | Formation of Sponge Park at Manali New Town Block 90 CPS-3 Park | 3 months | 100% | 0 | 7.4 | 7.4 | 1st & Final Bill received on 12.10.23
8 | 2 | 19 | Formation of Sponge Park at MMDA 2nd Main Road Park | 3 months | 100% | 0 | 6.65 | 6.65 | 1st & Final Bill received on 17.07.23
9 | 3 | 30 | Formation of Sponge Park at Secretariate Colony Park | 3 months | 100% | 0 | 2.79 | 2.79 | 1st & Final Bill received 2.8.23
10 | 4 | 47 | Formation of Sponge Park at Bharathi Nagar TNSCB park | 1month | 100% | 0 | 1.96 | 1.96 | 1st & Final Bill received on 04.9.23
11 | 4 | 36 | Formation of Sponge Park at TV Nagar 5th Street (Bharathi Park) | 3 months | 100% | 0 | 14.41 | 14.41 | 1st & Final Bill received on 8.8.23
12 | 4 | 40 | Formation of Sponge Park at Tsunami Park (B) Block, Tsunami Quarters | 3 months | 100% | 0 | 3.34 | 3.34 | 1st & Final bill received on 17.10.23
13 | 4 | 40 | Formation of Sponge Park at Elaya Park, Elaya street | 3 months | 100% | 0 | 16.55 | 16.55 | 1st & Final bill received on 21.12.23
14 | 4 | 40 | Formation of Sponge Park At Prince Village - Phase (I) | 3 months | 100% | 0 | 12.63 | 12.63 | 1st & Final bill received on 22.11.23
15 | 4 | 40 | Formation of sponge Park at Prince Village Phase (II) | 3 months | 100% | 0 | 16.52 | 16.52 | 1st & Final bill received on 22.11.23
16 | 5 | 51 | Formation of Sponge Park at MC road - Basement park | 3 months | 100% | 0 | 2.57 | 2.57 | 1st & final Bill received on 23.11.23
17 | 5 | 58 | Formation of Sponge Park at My Ladies Park | 3 months | 100% | 0 | 3.66 | 3.66 | 1st & final Bill received on 30.10.23
18 | 5 | 58 | Formation of Sponge Park at Jermiah Park | 3months | 100% | 0 | 1.79 | 1.79 | 1st & final Bill received on 13.2.24
19 | 5 | 62 | Formation of Sponge Park At Deputy Mayor Kabala Moorthy Salai, May Day Park | 3 months | 100% | 0 | 4.16 | 4.16 | 1st & final Bill received on 22.2.24
20 | 5 | 50 | Formation of Sponge Park at Sundaramurthy Park at Venkatesan Street | 3 months | 100% | 0 | 7.51 | 7.51 | Bill received
21 | 5 | 61 | Formation of Sponge Park at Mayor Sundar Rao Park Rukmani Lakshmipathy Salai | 3 months | 100% | 0 | 8.31 | 8.31 | 1st & final Bill received on 10.2.24
22 | 6 | 64 | Formation of Sponge Park at VV Nagar | 3 months | 100% | 0 | 13.65 | 13.65 | 1st & final bill received on 15.12.23
23 | 6 | 65 | Formation of Sponge Park at poompukar 4th street | 6 months | 100% | 0 | 13 | 13
24 | 6 | 68 | Formation of Sponge park at Periyar Nagar 20th street park | 6 months | 100% |  | 5.39 | 5.39 | 1st & Part bill received on 23.03.2024
25 | 6 | 68 | Formation of Sponge park at jawahar Nagar 5th street park | 6 months | 100% | 18.26 | 6.51 | 24.77 | 2nd & Final Bill Received On 2.09.2024
26 | 6 | 74 | Formation of Sponge park at Mursolimaran park south at Perambur High Road | 6 months | 100% | 13.47 | 3.13 | 16.6 | 2nd & Final Bill received on 3.11.23
27 | 7 | 84 | Formation of Sponge park at Periyavannan Kulam(Near Gangai Amman Koil Street) | 6 months | 100% |  | 35.43 | 35.43 | 1st & Final Bill Received on 21.01.2025
28 | 7 | 86 | Formation of SpongePark in OSR Park at Manikkam Pillai Street, Mannurpet | 9 months | 100% | 0 | 25.25 | 25.25 | 1st & part Bill Received On 30.03.2024
29 | 7 | 91 | Formation of Sponge Park at Babakulam | 6 months | 100% | 24.34 | 17.1 | 41.44 | 3rd & part Bill received on 15.03.2024 | Bil rev
30 | 8 | 100 | Formation of Sponge Park (Kencess Park) at E.V.R Lane | 3 months | 100% | 0 | 8.07 | 8.07 | 1st & final Bill received on 01.9.23
31 | 8 | 103 | Formation of Sponge Park and other improvement works at A D Block 3rd street park | 3 months | 100% | 0 | 5.41 | 5.41 | 1st & final Bill received on 13.9.23
32 | 8 | 104 | Formation of Sponge Park at of I-Block, 38th street | 3 months | 100% | 0 | 6.83 | 6.83 | 1st & final Bill received on 16.6.23
33 | 8 | 104 | Formation of Sponge Park at of I-Block, 2nd Street | 3 months | 100% | 5.37 | 0 | 5.37 | 1st & final Bill received on 13.9.23
34 | 9 | 109 | Formation of Sponge Park in Gill Nagar Park at Shanmuganar Salai, Kamarajar Nagar | 3 months | 100% | 0 | 5.54 | 5.54 | 1st & final Bill received on 4.9.23
35 | 9 | 111 | Formation of Sponge Park In Nungambakkam, 4th Lane | 3 months | 100% | 0 | 2.75 | 2.75 | 1st & final Bill received on 29.9.23
36 | 9 | 122 | Formation of Sponge Park at Turnbulls road | 3 months | 100% | 0 | 10.48 | 10.48 | 1st & final Bill received on 26.12.23
37 | 10 | 128 | Formation of Sponge Park in Lambert Nagar at 2nd Main Road | 3 months | 100% | 1.63 | 2.83 | 4.46 | 2st & final bill received on 28.06.2024
38 | 10 | 135 | Formation of Sponge Park at 12th Avenue Park | 3 months | 100% | 0 | 3.66 | 3.66 | 1st & final Bill received on 17.10.23
39 | 10 | 135 | Formation of Sponge Park at 14th Sector 102nd Street Park | 3 months | 100% | 0 | 4.61 | 4.61 | 1st & final Bill received on 17.10.23
40 | 11 | 143 | Formation of Sponge Park at VGN Nagar Channel Park | 3 months | 100% | 0 | 4.49 | 4.49 | 1st & final Bill received on 4.10.23
41 | 11 | 149 | Formation of Sponge Park at Brindhavana Nagar 5th Street park (Vartha Park) | 3 months | 100% | 0 | 7.7 | 7.7 | 1st & final part received on 04.10.23
42 | 12 | 156 | Formation of Sponge Park at Kalaimagal Nagar Park | 6 months | 100% | 9.58 | 1.74 | 11.32 | 2nd & Final Bill received on 03.05.2024
43 | 12 | 156 | Formation of Sponge Park at Thiruvallur Nagar Park | 3 months | 100% | 0 | 7.98 | 7.98 | 1st & final bill received on 18.10.23
44 | 12 | 156 | Formation of Sponge Park at Sindhu Salai Park | 3 months | 100% | 0 | 7.23 | 7.23 | 1st & final bill received on 18.10.23
45 | 12 | 156 | Formation of Sponge Park at Santhosh Nagar Ramachandran Street Park | 3 months | 100% | 0 | 8.09 | 8.09 | 1st & final bill received on 18.10.23
46 | 12 | 156 | Formation of Sponge park at Madha Nagar 2nd Main Road Park | 3 months | 100% | 0 | 7.09 | 7.09 | 1st & final bill received on 18.10.23
47 | 12 | 156 | Formation of Sponge Park at V.N.D Vaigai and Madha Nagar 17th street park | 3months | 100% | 0 | 5.34 | 5.34 | 1st & final bill received on 18.10.23
48 | 12 | 157 | Formation of Sponge Park at CRR puram Park | 3months | 100% | 0 | 7.18 | 7.18 | 1st & final bill received on 1.12.23
49 | 12 | 157 | Formation of Sponge Park at Kaviya Gardern Park | 3months | 100% | 0 | 6.15 | 6.15 | 1st & final bill received on 1.12.23
50 | 12 | 157 | Formation of Sponge Park at Bel Nagar Park | 3months | 100% | 0 | 6.23 | 6.23 | 1st & final bill received on 1.12.23
51 | 12 | 157 | Formation of Sponge park at Macro Marvel River View County Park | 3 months | 100% | 0 | 7.09 | 7.09 | 1st & final bill received on 1.12.23
52 | 13 | 177 | Formation of Sponge park at VGP Selva Nagar 2nd Main Road park | 3 months | 100% | 0 | 7.81 | 7.81 | 1st & part Bill received on 21.6.23
53 | 13 | 179 | Formation of Sponge park at Gangai Street Park | 3 months | 100% | 0 | 7.41 | 7.41 | 1st & final Bill received on 2.8.23
54 | 14 | 184 | Formation of Sponge Park at Telephone Nagar Park | 3 months | 100% | 0 | 4.94 | 4.94 | 1st & Final Bill received on 4.9.23
55 | 14 | 189 | Formation of Sponge Park at Kamakotti Nagar Ist Main Road Park | 3 months | 100% | 0 | 3.89 | 3.89 | 1st & Final Bill received on 6.11.23
56 | 15 | 200 | Formation of Sponge Park at Bharathi Nagar Main Road | 6months | 100% | 0 | 29.76 | 29.76 | 1st & final Bill received on 16.04.2024
57 | 15 | 200 | Formation of Sponge Park at Anna Salai 1st Cross Street | 6months | 100% | 0 | 36.94 | 36.94 | 1st & final Bill received on 16.04.2024

## 2024-25 Completed
2024-2025 Honarable Minister Announcement (Capital Fund)
SPONGE PARKS LINE LIST (COMPLETED)
Sl. No | Zone | Div | Location | Estimate (Rs. In Lakh) | Physical Progress (%) | Financial Progress
[6 empty] | Last Review Amt in Lakhs | Now Amt in Lakhs | Total Amt in Lakhs | Bill received
1 | 8 | 99 | Formation of Sponge Park (Nehru Park) at P.H.Road | 27.52 | 100% |  | 24.66 | 24.66 | 1st & Final Bill received on 29.03.2025
2 | 8 | 101 | Formation of Sponge Park for 'G"Block park at 2nd Avenue Extn. | 29.27 | 100% |  | 25.27 | 25.27 | 1st & Final Bill received on 29.03.2025
3 | 9 | 113 | Formation of Sponge Park at Sharma Park | 7.3 | 100% | 0 | 56.6 | 56.6 | 1ST & Final bill received on 03.06.2025
4 | 10 | 127 | Formation of Sponge park at SAF Games village, OSR | 13.8 | 100% | 0 | 11.85 | 11.85 | 1st & Final Bill received on 29.03.2025
5 | 10 | 136 | Formation of Sponge Park and allied works at Sivan Park | 9.4 | 100%
6 | 6 | 75 | Formation of Sponge park at Herbal Park,otteri | 27 | 100% |  | 23.21 | 23.21
7 | 11 | 143 | Proposed Construction of Sponge Park at Nolambur Phase-II 13th cross street, (Ration Shop Park) | 30 | 100%
8 | 11 | 143 | Proposed Construction of Sponge Park at Nolambur, Phase-I 3rd Main road | 30 | 100%
9 | 8 | 108 | Formation of Sponge Park at Mayor Sathiyamoorthy Salai | 27.52 | 100% |  | 23.49 | 23.49 | 1st & Part Bill received on 24.05.2025
10 | 12 | 167 | Formation of Sponge Park at State Bank Colony Park | 19 | 100%
11 | 5 | 57 | Formation of Sponge Park at Sri Ramulu Park at Parakasam Salai | 4.92 | 100%
12 | 5 | 58 | Formation of Sponge Park in Thirumalai Park at EVK Sampath Road | 2.4 | 100%
13 | 12 | 156 | Formation of Sponge Park at Sri Amman Nagar OSR Land | 13 | 100%
14 | 5 | 53 | Formation of Sponge Park to the Mint Park at North Wall Road | 9.92 | 100%
15 | 7 | 86 | Formation of Sponge park at Manickam Pillai Street, OSR | 124 | 100%
16 | 2 | 15 | Formation of Sponge park at Manali New Town Block no.26, CPS-10 | 11 | 100%
17 | 2 | 18 | Formation of Sponge park in CPCL layout park | 10 | 100%
18 | 2 | 18 | Formation of Sponge park in Nedunchezhiyan street | 10 | 100%
19 | 15 | 196 | Formation of Sponge Park at Annai Indra Nagar 1st Street | 34 | 100%
20 | 15 | 198 | Formation of Sponge Park at New Kumaran Nagar 2nd Main Road | 34.9 | 100%
21 | 15 | 200 | Formation of Sponge Park at TNUHDB 1st Main Road | 31 | 100%

## 2024-25 Ongoing list
2024-2025 Honarable Minister Announcement (Capital Fund)
SPONGE PARKS LINE LIST ONGOING
Sl. No | Zone | Div | Location | Estimate (Rs. In Lakh) | Physical Progress (%) | Financial Progress
[6 empty] | Last Review Amt in Lakhs | Now Amt in Lakhs | Total Amt in Lakhs | Bill received
19 | 4 | 35 | Proposed construction sponge park and Reconstruction of Motor room Muthamil nagar 9th street | 31.1 | 80%
20 | 4 | 37 | Construction of Sponge Park and Construction of Motor Room at Jawahar Street | 31.1 | 70%
21 | 4 | 37 | Construction of Sponge Park and Construction of Motor Room at Sasirekkamma Nagar | 31.1 | 70%
22 | 4 | 47 | Proposed Construction of sponge park at Bharathi Nagar TNSCB | 29.4 | 90%
23 | 4 | 47 | Proposed Construction of Sponge Park at Amma Eco Park, C.B.Road | 29.4 | 90%
24 | 15 | 193 | Formation of Sponge Park at Sri Sai Nagar 2nd Main Road | 36 | 99%
26 | 15 | 197 | Formation of Sponge Park at VGP South Main Road | 18.8 | 98%
27 | 15 | 197 | Formation of Sponge Park at Bakthi Vedandha Salai | 14.5 | 97%
30 | 3 | 31 | Formation of Sponge park at Ranga Avenue | 75.8 | 91%